## Risk Register
Risk ID | Asset | Risk Description | Root Cause | Likelihood (1-5) | Impact (1-5) | Risk Score | Recommended Treatment | Control ID | Risk Owner | Date Identified | Status | Evidence | Notes
R-001 | Ubuntu Workstation | Unrestricted inbound connections may increase attack surface | Host-based firewall (UFW) was inactive — no deny-inbound policy enforced at endpoint layer | 3 | 3 |  | Enable UFW with default deny-inbound policy and verify configuration is persistent across reboots | SC-7 | System Owner | 2026-01-29 | Closed | evidence/ufw-status-enabled.txt | Remediated — UFW enabled with deny inbound / allow outbound baseline. Verified post-remediation.
R-002 | Ubuntu Workstation | Known vulnerabilities may be exploited due to unpatched software | No documented patch cadence — patches are applied reactively without a defined schedule | 4 | 3 |  | Implement weekly patch cadence and retain dated apt logs as evidence of completion | SI-2 | System Owner | 2026-01-29 | Open | evidence/journal-warnings-7d.txt | Apt activity observed in journal — patching is occurring but not documented or scheduled
R-003 | Ubuntu Workstation | Excess privileged group membership may enable unauthorized packet capture or system changes | User klowry86 holds wireshark group membership (packet capture privileges) not documented as justified | 3 | 4 |  | Document wireshark group membership as justified exception or remove; conduct quarterly group review | AC-6 | System Owner | 2026-01-29 | Open | evidence/current-user-id.txt | klowry86 is member of wireshark group granting packet capture without sudo
R-004 | Ubuntu Workstation | Hardening gaps may persist without routine log review | Netplan config file permissions are too open and no routine log review process is documented | 2 | 2 |  | Fix netplan file permissions (chmod 600) and implement documented weekly log review with evidence | AU-6 | System Owner | 2026-01-29 | Open | evidence/journal-warnings-7d.txt | Netplan permission warning is actionable; remaining warnings are informational
R-005 | Ubuntu Workstation | Data loss may occur without validated backup and recovery capability | No backup process, schedule, or restore test has been implemented for sensitive or internal data | 3 | 4 |  | Implement weekly automated backup to external/cloud destination and conduct monthly restore test | CP-9 | System Owner | 2026-01-29 | Open | No backup evidence collected | Highest availability risk — no recovery path exists without backup

## Legend
RISK SCORE LEGEND
Score 1-4 | Low Risk — monitor
Score 5-9 | Moderate Risk — remediate in next cycle
Score 10-25 | High Risk — prioritize remediation
SCORING METHOD | Likelihood (1-5) × Impact (1-5)
STATUS
Open | Finding not yet remediated
Closed | Finding remediated with evidence