## POA&M
POA&M ID | Risk ID | Control ID | Weakness Description | Planned Remediation | Milestone Date | Validation Method | Responsible Party | Status | Date Opened | Date Closed | Notes
P-001 | R-001 | SC-7 | Host-based firewall (UFW) was inactive — no deny-inbound policy enforced at endpoint layer | Enable UFW and configure default deny-inbound / allow-outbound policy; verify persistence across reboots and document configuration | 2026-02-15 | evidence/ufw-status-enabled.txt confirms Status: active with deny incoming / allow outgoing baseline | System Owner | Closed | 2026-01-29 | 2026-02-15 | Remediated on schedule — UFW enabled with correct baseline. Evidence collected and retained.
P-002 | R-002 | SI-2 | No documented patch cadence — patches applied reactively without schedule or retained evidence | Apply all available updates weekly; retain dated apt update and upgrade output logs as evidence; prioritize security updates | 2026-03-15 | Dated apt log files saved to evidence folder showing upgradable package count at zero after update cycle | System Owner | Open | 2026-01-29 |  | Apt activity observed in system journal — patching is occurring but must be formalized with retained evidence
P-003 | R-003 | AC-6 | User klowry86 holds wireshark group membership granting packet capture privileges — not documented as justified exception | Document wireshark group membership as deliberate justified exception with stated purpose; remove if not actively required; conduct quarterly group membership review | 2026-03-20 | Written justification or removal documented and dated; current-user-id.txt reviewed and approved | System Owner | Open | 2026-01-29 |  | Wireshark group membership is likely intentional for coursework — must be documented as exception or removed
P-004 | R-004 | AU-6 | Netplan configuration file permissions too open (world-readable); no documented routine log review process | Remediate netplan permissions with chmod 600; implement and document weekly log review; retain dated log excerpts as review evidence | 2026-03-25 | Netplan permission warning no longer present in journal after chmod; weekly log review files retained with dates | System Owner | Open | 2026-01-29 |  | All other journal warnings assessed as informational — netplan permission is the only actionable hardening item
P-005 | R-005 | CP-9 | No backup process or restore test implemented — sensitive and internal data has no recovery path | Implement weekly automated backup using Deja Dup or rsync to external or cloud destination; conduct monthly restore test and retain test result evidence | 2026-03-30 | evidence/backup-run.txt (backup log) and evidence/restore-test.txt (restore test result) collected and dated | System Owner | Open | 2026-01-29 |  | Highest-impact open item — no evidence collected yet; backup implementation is priority remediation action

## Summary
POA&M Summary
Total Items | 5
Closed | 1
Open | 4
Highest Priority | P-005 — CP-9 Backup (no evidence)
Assessment Date | February 2026
Assessor | Kenneth Lowry
Framework | NIST SP 800-53 Rev 5